## Product Backlog
4 | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | Collect healthcare operational datasets | Must | None | JOEL JIBY | Completed
Sprint 1 | Sprint 1 | US-02 | Clean and preprocess admissions and patient data | Must | US-01 | JOEL JIBY | Completed
Sprint 1 | Sprint 1 | US-03 | Handle missing values, duplicates and data types | Must | US-02 | JOEL JIBY | Completed
Sprint 1 | Sprint 1 | US-04 | Select relevant attributes for operational analysis | Must | US-01 | JOEL JIBY | Completed
Sprint 1 | Sprint 1 | US-05 | Create integrated cleaned dataset | Must | US-02, US-04 | JOEL JIBY | Completed
Sprint 1 | Sprint 1 | US-06 | Define and validate healthcare KPIs | Must | US-05 | JOEL JIBY | Completed
Sprint 2 | Sprint 2 | US-07 | Analyze patient admissions and discharge trends | Must | US-05 | JOEL JIBY | Completed
Sprint 2 | Sprint 2 | US-08 | Analyze treatment demand and departmental workload | Must | US-05 | JOEL JIBY | Completed
Sprint 2 | Sprint 2 | US-09 | Build patient flow visualizations | Must | US-06, US-07 | JOEL JIBY | Completed
Sprint 2 | Sprint 2 | US-10 | Identify operational bottlenecks and high-demand areas | Should | US-07, US-08 | JOEL JIBY | Completed
Sprint 3 | Sprint 3 | US-11 | Calculate bed utilization and capacity metrics | Must | US-05, US-06 | JOEL JIBY | Completed
Sprint 3 | Sprint 3 | US-12 | Analyze workforce and staffing efficiency | Must | US-05, US-06 | JOEL JIBY | Completed
Sprint 3 | Sprint 3 | US-13 | Create resource performance scorecards | Must | US-11, US-12 | JOEL JIBY | Completed
Sprint 3 | Sprint 3 | US-14 | Compare utilization with defined operational benchmarks | Should | US-11, US-13 | JOEL JIBY | Completed
Sprint 4 | Sprint 4 | US-15 | Build patient distribution geographic analysis | Must | US-05 | JOEL JIBY | Completed
Sprint 4 | Sprint 4 | US-16 | Build healthcare service coverage analysis | Should | US-15 | JOEL JIBY | Completed
Sprint 4 | Sprint 4 | US-17 | Integrate patient flow and resource intelligence | Must | US-09, US-13 | JOEL JIBY | Completed
Sprint 4 | Sprint 4 | US-18 | Build executive dashboard with key operational KPIs | Must | US-17 | JOEL JIBY | Completed
Sprint 4 | Sprint 4 | US-19 | Add interactive filters and dashboard navigation | Must | US-18 | JOEL JIBY | Completed
Sprint 4 | Sprint 4 | US-20 | Deploy and test complete dashboard | Must | US-18, US-19 | JOEL JIBY | Completed
Sprint 4 | Sprint 4 | US-21 | Validate KPIs, filters, calculations and data consistency | Must | US-20 | JOEL JIBY | Completed
Sprint 4 | Sprint 4 | US-22 | Document project and prepare final presentation | Should | US-20, US-21 | JOEL JIBY | Completed
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 50 | 10 | 8 | 9 | 9 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-01 | T-01 | Identify and collect relevant healthcare datasets |  |  | JOEL JIBY | Data Collection | Completed | 6 | Day 1: 6
US-01 | T-02 | Review dataset structure, columns and data quality |  |  | JOEL JIBY | Data Analysis | Completed | 4 | Day 1: 4
US-02 | T-03 | Load raw datasets using Pandas |  |  | JOEL JIBY | Data Processing | Completed | 3 | Day 2: 3
US-02 | T-04 | Handle missing values and duplicates |  |  | JOEL JIBY | Data Cleaning | Completed | 5 | Day 2: 5
US-03 | T-05 | Standardize dates, categorical values and data types |  |  | JOEL JIBY | Data Cleaning | Completed | 5 | Day 3: 5
US-04 | T-06 | Select relevant columns for project KPIs |  |  | JOEL JIBY | Data Analysis | Completed | 4 | Day 3: 4
US-05 | T-07 | Merge related datasets where required |  |  | JOEL JIBY | Data Integration | Completed | 6 | Day 4: 6
US-05 | T-08 | Export cleaned/processed dataset |  |  | JOEL JIBY | Data Processing | Completed | 3 | Day 4: 3
US-06 | T-09 | Define Total Patients, Admissions, Discharges and LOS KPIs |  |  | JOEL JIBY | KPI Definition | Completed | 5 | Day 5: 5
US-06 | T-10 | Validate KPI calculations against source data |  |  | JOEL JIBY | Validation | Completed | 4 | Day 5: 4
US-05 | T-11 | Create project repository and folder structure |  |  | JOEL JIBY | GitHub | Completed | 2 | Day 6: 2
US-05 | T-12 | Update README with data pipeline and setup instructions |  |  | JOEL JIBY | Documentation | Completed | 3 | Day 6: 3
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Dataset structure and data quality needed review | Reviewed source fields and confirmed the data needed for healthcare operations analysis.
Sprint 1 | Day 2 | Inconsistent formats and missing values | Standardized fields and applied cleaning/validation rules.
Sprint 1 | Day 3 | Duplicate/irrelevant records required checking | Reviewed duplicates and retained only appropriate records.
Sprint 1 | Day 4 | KPI definitions needed validation | Defined operational KPIs and checked calculations against source data.
Sprint 2 | Day 1 | Patient and admission analysis required refinement | Built and validated admissions, patient and treatment analysis.
Sprint 2 | Day 2 | Visual selection needed to avoid clutter | Selected KPI cards and focused charts for operational decision-making.
Sprint 2 | Day 3 | Cross-filter behaviour required checking | Tested slicers, interactions and page-level filtering.
Sprint 2 | Day 4 | Departmental/resource analysis needed consistency | Aligned resource and workload measures with the same operational definitions.
Sprint 3 | Day 1 | Bed/resource utilization calculations required validation | Validated bed and resource utilization measures and visual outputs.
Sprint 3 | Day 2 | Staff metrics needed comparison | Reviewed staff-efficiency measures and workload indicators.
Sprint 3 | Day 3 | Bottleneck views needed clearer presentation | Refined resource-utilisation and bottleneck visuals.
Sprint 3 | Day 4 | Executive summary needed concise KPIs | Consolidated key operational indicators into executive-level views.
Sprint 4 | Day 1 | Multiple dashboard pages required consistent navigation | Reviewed page structure and navigation across the completed report.
Sprint 4 | Day 2 | Geographic/service analysis required final validation | Checked geographic and healthcare-service analysis against available fields.
Sprint 4 | Day 3 | Final KPI/filter consistency check | Retested major KPIs, slicers, filters and calculations.
Sprint 4 | Day 4 | Documentation and presentation preparation | Recorded testing outcomes, defects/resolutions and final project documentation.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 |  |  | Project Team | Start documenting data assumptions earlier | Stop making untracked data changes | Continue validating data before visualization | Data cleaning and KPI assumptions were documented and checked.
2 | Sprint 2 |  |  | Project Team | Start validating visuals immediately after creation | Stop adding visuals without a decision purpose | Continue using focused operational KPIs | Patient, admission, treatment and workload analysis were consolidated.
3 | Sprint 3 |  |  | Project Team | Start cross-checking resource metrics earlier | Stop leaving filter testing until the end | Continue checking calculations against source data | Resource, bed and staff views were validated and refined.
4 | Sprint 4 |  |  | Project Team | Start preparing final documentation alongside testing | Stop treating documentation as a final-only task | Continue systematic KPI and interaction testing | Final dashboard review, testing and documentation were completed.