## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Project Team | Executive Dashboard | KPI value did not refresh as expected after a filter was applied. | Sprint 4 | Project Team | Logical | Reviewed the filter context and KPI measure configuration; corrected the filtering logic. | High | High | Closed | Retested with filters; KPI updated correctly.
2 | Project Team | Patient Analytics | Patient count displayed inconsistently between an overview visual and a filtered patient view. | Sprint 4 | Project Team | Logical | Checked aggregation and filter context and aligned the calculation with the intended patient-count logic. | High | High | Closed | Values were consistent after retesting.
3 | Project Team | Admissions Analytics | Admissions trend did not respond correctly to the selected date filter during validation. | Sprint 4 | Project Team | Logical | Reviewed date filtering and corrected the relevant date/filter configuration. | High | High | Closed | Date-filter behaviour verified.
4 | Project Team | Treatment Analytics | Treatment visual required correction to ensure the displayed aggregation matched the underlying data. | Sprint 3 | Project Team | Logical | Validated the aggregation and corrected the visual/measure configuration. | Medium | High | Closed | Treatment values matched the validated calculation.
5 | Project Team | Facilities Analytics | A facilities-related visual required adjustment for clearer interpretation of the displayed measure. | Sprint 3 | Project Team | User Interface | Updated the visual configuration and presentation labels. | Low | Medium | Closed | Visual reviewed and accepted.
6 | Project Team | Staff Analytics | Staff workload/efficiency visual required validation after changes to filters. | Sprint 3 | Project Team | Logical | Checked filter interactions and recalculated the affected metric. | Medium | High | Closed | Metric responded correctly after retesting.
7 | Project Team | Resource Utilisation | Bed/resource utilization indicator required calculation validation. | Sprint 3 | Project Team | Logical | Cross-checked the utilization calculation against the source values and corrected the measure configuration. | High | High | Closed | Utilization indicator passed validation.
8 | Project Team | Resource Utilisation | Resource bottleneck visual required clearer labels to distinguish operational categories. | Sprint 3 | Project Team | User Interface | Revised titles/labels and formatting for clarity. | Low | Medium | Closed | Labels were reviewed for readability.
9 | Project Team | Executive Summary | Summary indicators required consistency checking against detailed dashboard pages. | Sprint 4 | Project Team | Logical | Compared summary measures with the corresponding detailed-page measures and aligned the calculation/filter context. | High | High | Closed | Summary values were consistent after correction.
10 | Project Team | Dashboard Navigation | Navigation between report pages required validation to ensure every page opened correctly. | Sprint 4 | Project Team | Functional | Reviewed page navigation and tested each report page. | Medium | Medium | Closed | All tested pages opened correctly.
11 | Project Team | Dashboard Filters | Slicer/filter interaction caused unexpected changes in a related visual during testing. | Sprint 4 | Project Team | Functional | Reviewed visual interactions and adjusted the affected interaction settings. | Medium | High | Closed | Slicer interactions behaved as intended after retesting.
12 | Project Team | Dashboard Layout | Some chart titles/labels required formatting adjustments for readability. | Sprint 4 | Project Team | User Interface | Adjusted titles, labels and visual formatting. | Low | Low | Closed | Dashboard reviewed at normal viewing size.
13 | Project Team | Executive Dashboard | A KPI card needed clearer naming to avoid ambiguity for the end user. | Sprint 4 | Project Team | User Interface | Updated KPI label/title to describe the measure more clearly. | Low | Medium | Closed | KPI naming reviewed and accepted.
14 | Project Team | Patient Analytics | Demographic visual required filter-response verification. | Sprint 4 | Project Team | Functional | Applied relevant filters and checked that demographic visuals responded consistently. | Medium | Medium | Closed | Filter response verified.
15 | Project Team | Admissions Analytics | Admissions-related visual required consistency verification after dashboard updates. | Sprint 4 | Project Team | Logical | Rechecked the visual against the validated admissions calculation. | Medium | Medium | Closed | Visual passed final validation.
16 | Project Team | Resource Utilisation | Bed availability/utilization presentation required final review for readability. | Sprint 4 | Project Team | User Interface | Reviewed labels, values and layout in the resource-utilization page. | Low | Medium | Closed | Final presentation reviewed successfully.
17 | Project Team | Executive Summary | Executive summary layout required refinement to keep key indicators easy to scan. | Sprint 4 | Project Team | User Interface | Adjusted visual arrangement and spacing. | Low | Medium | Closed | Summary page reviewed successfully.
18 | Project Team | Overall Dashboard | Final report required a complete regression check after corrections were applied. | Sprint 4 | Project Team | Regression | Retested major KPIs, filters, navigation and operational analysis pages. | High | High | Closed | Regression testing completed with documented test cases passed.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others